# PerX Project Progress Report

## Overview of Project

The PerX project has developed a Pilot service which provides subject resource discovery across a series of repositories of interest to the engineering learning and research communities. This pilot is being used as a test-bed to explore the practical issues that would be encountered when considering the possibility of full scale subject resource discovery services.

Issues being investigated include: the range and availability of actual and potential digital repository sources; exploration of cultural barriers to the use of repositories in the subject community, functionality of software tools; advocacy to encourage participation of repository providers; maintenance issues; interactions with infrastructural shared services; enhancing metadata quality; embedding and reuse of resource discovery services; improving search and browse results presentation; service profiling for particular audiences, and service sustainability.

### Grant Statement

We confirm that the project is being conducted under the terms agreed with JISC in the letter of grant of 13th May 2005 and the JISC Terms and Conditions attached to it.

### 2. Aims and Objectives

There has been a change to one of the original aims outlined in the project plan – Aim 4: “To investigate improved methods of resource discovery within a subject-based cross-repository search tool. Objective [3]: Trial Adaptive Concept Mapping techniques for facilitating retrieval of resources within the pilot.”  As one of the original partners in the PerX Project, Adiuri Systems Ltd, who were to supply the Adaptive Concept Mapping software, went into receivership, it will no longer be possible to reach this Objective.  Instead, and as detailed in a Change Report submitted to, and agreed with, the DRP Project Manager, additional work on metadata available from several repositories will be undertaken, and additional effort to that originally anticipated in the development of the Pilot cross-search software has already been undertaken.

Objective: Review and analyse the current digital repository landscape within engineering, and identify repository sources with a view to informing the development of a pilot service.

This Objective has been met.

Objective: Set up a pilot subject-based cross-repository search tool for resource discovery.

This Objective has been met.

Objective: Using the pilot subject-based cross-repository search tool as a testbed, ascertain from a selection of academic end-users in engineering their opinions on the appropriateness of the subject-based approach to resource discovery, and the effectiveness of different versions of the pilot.

This Objective has been partially met, and the first version of the Pilot has been used as a testbed.  An improved version is being developed and will also be evaluated with end-users.

Objective: Monitor, quantify and document the technical and management effort required during the pilot.

Procedures have been put in place to monitor this effort, and monitoring is proceeding.

Objective: Investigate and implement automatic methods of harvesting repositories.

This Objective is partially complete. Completion has been delayed due to the delayed availability of the Pilot software (see below under 7. Risk Analysis: Software).

Objective: Analyse suitability of JISC shared infrastructural services for use within the pilot, and experiment with the incorporation of a minimum of two.

This Objective is partially complete.

Objective: Identify a number of potential source repositories, and work with them to understand their needs and encourage their participation.

This Objective is partially complete.  A number of potential source repositories have been identified, contact has been made with several, and work is continuing with them.

Objective: Produce advocacy materials aimed at potential data providers.

This Objective has been met.

### 3. Overall Approach

There are no changes to the overall approach outlined in the project plan.

### 4. Project Outputs

Project Plan.

Delivered. Available on request to: R.A.MacLeod@hw.ac.uk

Project Website.

Delivered.  Available at: http://www.icbl.hw.ac.uk/perx/

Review of the existing current digital repository landscape (publications, projects, services, initiatives) within engineering.

Delivered.  Engineering Digital Repositories Landscape Analysis, and Implications for PerX: available at: http://www.icbl.hw.ac.uk/perx/analysis.htm

List of currently available and relevant digital repositories of interest to engineering, potential digital repository sources, and gap areas.

Delivered.  Listing of Engineering Repository Sources: available at: http://www.icbl.hw.ac.uk/perx/sourceslisting.htm

Basic pilot engineering cross-search service, populated with identified repository targets.

Delivered.  http://www.engineering.ac.uk  The Project experienced some unanticipated problems with the SPP software used for the planned cross-search service.  These required additional effort and the development of new software.

Progress Report for first six months.

Delivered. Available on request to: R.A.MacLeod@hw.ac.uk

Reports from Focus Groups/interviews with users and questionnaire, detailing end-user opinion on the appropriateness of the subject-based approach to resource discovery, the range of different types of materials available in the pilot cross-search service, and gaps in coverage.

Partially delivered.  A report from one Focus Group is available on request to: R.A.MacLeod@hw.ac.uk

Other Focus Groups, to be organised by PerX Partners, have not yet been held.  Results of the questionnaire will be available shortly.

Advocacy materials which explain the approaches to, and benefits of, enabling resource discovery in multiple repositories.

Delivered.  'Marketing' with Metadata - How Metadata Can Increase Exposure and Visibility of Online Content. Version 1.0 8th March 2006 M.Moffat. Available at: http://www.icbl.hw.ac.uk/perx/advocacy/exposingmetadata.htm

Advocacy work with potential target repositories is ongoing.

### 5. Project Outcomes

The two documents - Listing of Engineering Repository Sources; and the Engineering Digital Repositories Landscape Analysis, and Implications for PerX - have provided a better understanding and knowledge of the digital repository landscape in engineering, including gap areas, and have also identified other issues of potential interest to the wider digital repository community.  These has been communicated to others in the DRP.  Comments received about the documents have been supportive.

More repositories of potential interest to the engineering community are likely to be available in the near future.

Publicising the two deliverables mentioned above, along with the PerX website, the ‘Marketing with metadata…’ document, and the position of the PerX Project within the DRP, has begun the process of increasing awareness within the engineering community of the benefits of digital repositories.  Material about PerX and its deliverables has appeared in a number of external publications, including D-Lib, E-MmITS, FreePint, ResourceShelf, CurrentCites, UKSG Serials-eNews, eLucidate, and Library + Information Update.  The availability of the TechXtra service, an initiative of Heriot-Watt University, and not funded by the JISC, is encouraging practical resource discovery from repositories in engineering, maths and computing.

PerX has input into the UK IR Search proposal.

A paper presented by Santy Chumbe, the PerX Technical Officer (2nd International Conference on Computer Science and Information Systems, Athens, Greece, 9th June 2006 - Overcoming the obstacles of harvesting and searching digital repositories from federated searching toolkits, and embedding them in VLEs. http://eprints.rclis.org/archive/00006394/ ) includes information on the functionality offered by some software tools.

Knowledge of end-user opinion on subject-based resource discovery services has been gained from questionnaire feedback on the Pilot and from Focus Groups.

Experience of using shared services (IESR) is being gained.

More knowledge about the maintenance effort required for subject-based services is being gained.

Progress made so far has not changed the project, although the potential number of suitable targets has been revealed as very large.

Lessons for other projects in the DRP and elsewhere include those arising from the conclusions of the PerX Engineering Digital Repositories Landscape Analysis, and Implications for PerX.  These are available at: http://www.icbl.hw.ac.uk/perx/analysis.htm#conclusions

To summarise:

Subject based approaches to resource discovery of materials in repositories have considerable merit, though there are important differences between disciplines.

Any potential service which aims to facilitate resource discovery from repositories must take into account the differing nature of various information environments.

There are significant gap areas in coverage in the engineering repository landscape, including Research data, Subject Based Access, Technical Reports, Journals, and Assessment Materials repositories.

Identification of suitable repositories is difficult.  There is a need for better collection level descriptions.

There are many relevant repository sources which are multidisciplinary in nature, and many offer no effective means to subdivide collections on a subject basis.

Interoperability levels vary.

Advocacy work aimed at data providers is needed, and the adoption of broad subject sets by data providers, or alternatives to assist service providers identify relevant subject content, should be encouraged.

Usability of discovery services is important to ensure buy-in.

What has also become apparent is the fact that commercial publishers often have bespoke methods of metadata exchange (e.g. via FTP, Custom XML Schemes), with a range of partner organisations (e.g. Aggregators, Seach engines etc).  Our experience is showing that persuading publishers to adopt standardised interoperable approaches (e.g. OAI-PMH) in addition to their well established means of metadata exchange, is an uphill struggle.

### 6. Stakeholder Analysis

Amongst the producers of digital repositories included in the Pilot, PerX has been in contact with ARROW, Copac, CSA, EEVL/Intute, ePrints UK, GROW, HE Academy, Inderscience, IoP, JORUM, NDLTD and SearchLT.

Availability of the deliverables mentioned above has been promoted to some JISC email lists.

Information has been supplied to the JISC-funded Linking UK Repositories Scoping Study (Key Perspectives).

PerX has participated in the JISC-funded STARGATE Project.

A number of publishers have been alerted to PerX aims, and the possibilities arising from exposing their data to the Pilot.  These include the ICE, Emerald, Taylor & Francis, IEEE, IHS, RS, Morgan & Claypool, IStructE, University-technology.com, and CARL.

A proportion of Information Professionals/Subject Librarians and Researchers have been alerted to the aims of PerX via announcements to lists, public presentations and notices in some publications.

The RDN (now Intute) has been kept informed about PerX deliverables.

### 7. Risk Analysis

Hardware.

One hardware problem was experienced – In October the file system on the EEVL server which hosts PerX was found to be corrupt.  The system was reformatted.

In November there was a security problem with the EEVL server.  This was fixed.

As a result of staff loss at EEVL, the server on which PerX software resides no longer has a webmaster.  The PerX Technical Officer has therefore been burdened with these additional duties.  At some time in the future, the EEVL server, on which PerX resides, will no longer be maintained by Intute.  This has implications for PerX in that no funding for maintenance was included in the original Plan.

Software.

The decision by JISC to approve funding for the maintenance/development of the SPP software which is used for the PerX Pilot cross-search was not made until December 2005.  Funding was approved from March 06 to March 07.  Waiting on developments to the SPP software before developing a Pilot would have seriously delayed the PerX Project, therefore a new software package (PerX toolkit) was developed by the PerX Technical Officer, along with a PerX Pilot service infrastructure.

A set of tasks and a timescale has been agreed with ILRT for work which they will carry out to the SPP software.  This is needed for the second stage of the PerX Pilot.

### 8. Standards

No change.

### 9. Technical Development

Changes are detailed above under Risk Analysis: Software.  A Perx Administrative Interface (PAIN) has been developed which will simplify administrative changes to the Pilot.

### 10. Intellectual Property Rights

We are seeking a Memorandum of Understanding with the IEEE in order to allow harvesting of IEEE Xplore metadata.

## Project Resources

### 11. Project Partners

One project partner (GROW) has been informed that it will not be funded by the NSDL in 2006. However, GROW intends to continue to work with PerX as per the partner agreement.

PerX has co-operated with the STARGATE Project http://www.cdlr.strath.ac.uk/stargate/ which was funded by JISC and based at the CDLR.  The STARGATE project has explored the use of static repositories as a means of exposing publisher metadata to OAI-based disclosure, discovery and alerting services within the JISC Information Environment and beyond.  Four static repositories were produced by STARGATE (for the journals: Information Research, Information Scotland, Journal of Digital Information and Library and Information Research) and were included in the TechXtra cross-search which uses similar software as the Pilot.

PerX is hoping to agree a Memorandum of Understanding with the IEEE in order to allow harvesting of IEEE Xplore metadata within the PerX Pilot.

Informal briefings about PerX progress were given at SISSWG (Science Information Strategy for Scotland Working Group) meetings, by the PerX Manager, who is a member of SISSWG.

A proposal has been made to representatives of the ICE to develop a Civil Engineering Cross-Search Demonstration Service.

One of the original partners in PerX, Adiuri Systems Ltd, went into receivership.  The impact this had on the project is detailed above under: Aims and Objectives.

### 12. Project Management

Regular meetings of the Project staff have been held.

### 13. Programme Support

The PerX Manager attended the JISC Programme Meeting 7/8 July, Cambridge.  A PerX poster was made available at this meeting, and the Manager attended sessions chaired by the Programme Manager, Neil Jacobs.

The PerX Manager and the PerX Project Officer attended the Joint Programme Meeting: Digital Preservation & Asset Management and Digital Repositories, 10th October, Glasgow.

The PerX Manager attended the Second Digital Repositories Programme Meeting, 27-28 March, 2006.

Julie Allison, DRP Support, made a site visit to PerX 14 Feb, 2006.

### 14. Relationships with other projects activities

PerX has had contacts with SHERPA Plus, IESR (with which a proposal for a schedule of work was agreed and is being carried out), STARGATE (see above for details), ARROW and NDLTD (to discuss possible use of Sets), HE Academy Engineering/Materials (their database of learning materials is included in the Pilot cross-search), UK Web Archiving Consortium (the PerX website has been archived), UK Centre for Legal Education, the Digital Library Federation (which will use the PerX Repository Content Type Table synopsis in a study), and NEMLAC (who requested a copy of the ‘Marketing with metadata…’ document for their information site).

### 14. Budget

See Appendix A.

## Detailed Project Planning

### 15. Workpackages

Task 1. Review existing publications, projects, services and initiatives.

Completed.

Task 2. Gather and collate information.

Completed.

Task 3. Identification of currently available and relevant digital repositories.

Completed.

Task 4. Identification of potential digital repository sources/providers which are currently not available for federated searching.

Completed.

Task 5. Identification of obvious gaps in digital repository provision within engineering.

Completed.

Task 6. Set up a resource discovery service using SPP software.

Completed

Task 7. Add identified repository targets.

Completed.

Task 8. Ongoing support, development and debugging.

Completed.

Task 9. Plug-in of relevant toolkits into the pilot service infrastructure.

Completed.

Task 10. Set-up of repository targets to enable them to be utilised by plugged in toolkits.

Completed.

Task 12. Identify representatives of stakeholder groups (lecturers, researchers, students, FE/HE, information professionals).

Completed.

Task 13. Hold focus groups and interviews with users, and make questionnaire available on website.

Partially completed.  One Focus Group has been held, questionnaire has been made available.

Task 14. Document user experience and views.

Partially completed.  Reports will be available shortly.

Task 15. Produce advocacy materials.

Completed.

Task 16. Work with a range of potential data providers to better understand issues.

Partially completed, and also ongoing.

Task 18. Investigate available tools for automatically reharvesting of OAI Content (e.g. NSDL automated ingestion system).

Completed.

Task 20. Consider maintenance issues relating to distributed search targets (e.g. Z39.50).

Completed.

Task 21. Work with IESR to utilise up to date target information from central registry.

Partially complete.  Delayed by unanticipated work required on Pilot software.

Task 24. Ongoing monitoring of current trends in interoperability standards.

This is ongoing.

Task 28. Identify all relevant infrastructural shared services & develop potential usage scenarios.

Partially completed.

Objectives for the next reporting period:

Investigate and implement automatic methods of harvesting repositories.

Identify a number of potential source repositories, and work with them to understand their needs and encourage their participation.

Consider methods of metadata enhancement, and implement if appropriate.

Add new repositories to the pilot subject-based cross-repository search tool.

Embed the pilot search tool within a VLE.

Enable reuse and tailoring of search results by users.

### 16. Evaluation Plan

In order to evaluate the two documents: Engineering Digital Repositories Landscape Analysis, and Implications for PerX and the Listing of Engineering Repository Sources, their availability was announced in various lists (see under Dissemination below).  The responses received have been valid and generally very supportive of the documents’ content and viewpoints.

The Pilot cross-search service has been evaluated via one Focus Group, and an online 60 Second Survey (online questionnaire).  Results are currently being collated.  It is anticipated that the 60% positive measure of success will be achieved.

The measurement of success for the advocacy materials (1,000 hits) was reached very quickly.  By the end of the reporting period, there had been 4,104 hits to the materials.

Evaluation objectives for the next reporting period include: Seeking peer review of shared service usage scenarios.

### 17. Quality Assurance Plan

The PerX website has been delivered using HTTP 1.1 and designed using valid XHTML 1.0 and valid CSS.

Distributed searching is utilising Z39.50.

Metadata harvesting is as defined by OAI-PMH.

The PerX website has achieved positive WAI test results.

PerX will hope to utilise SRW/SRU in the next reporting period.

### 18. Dissemination Plan

The PerX project was announced in the lead partner’s university newsletter.

Informal updates were given to the RDN (now Intute) Executive Manager.

The Project Website was made available in September 2005, and the Pilot from March 2006. Hits to the two websites:

|  | PerX Website |  | Pilot Cross-search |  | Total Hits |
| --- | --- | --- | --- | --- | --- |
|  | Hits | Visits | Hits | Visits |  |
| Sept 2005 | 1006 | 306 |  |  | 1006 |
| Oct 2005 | 1228 | 277 |  |  | 1228 |
| Nov 2005 | 5243 | 865 |  |  | 5243 |
| Dec2005 | 2621 | 511 |  |  | 2621 |
| Jan 2006 | 4339 | 713 |  |  | 4339 |
| Feb 2006 | 2556 | 513 |  |  | 2556 |
| Mar 2006 | 16612 | 2451 | 1456 | 179 | 18,068 |
| Apr 2006 | 14671 | 2317 | 13376 | 1125 | 28,047 |
| May 2006 | 12216 | 1953 | 12140 | 1421 | 14,169 |
| Total |  |  |  |  | 77,277 |

The Project website, and the availability of the first two PerX outputs, was announced in the Internet Resources Newsletter, and was featured in a number of publications, including: Open Access News; KnowledgeSpeak; Technology Blog; STLQ; Eng Lib; e3 Information Overload; OA Librarian; JISC News; jisc-drp; jisc-repositories; eldnet-l; lis-scitech; engineering-all; cetis-metadata.

Material about PerX, the Pilot and other deliverables has appeared in a number of other publications, including D-Lib, E-MmITS, FreePint, ResourceShelf, CurrentCites, UKSG Serials-eNews, eLucidate, and Library + Information Update.

A presentation was given at Online Information 2005, which featured the PerX Project.

A paper was presented at the 2nd International Conference on Computer Science and Information Systems, Athens, Greece, 9th June 2006 - Overcoming the obstacles of harvesting and searching digital repositories from federated searching toolkits, and embedding them in VLEs. http://eprints.rclis.org/archive/00006394/

The RDN (now Intute) Executive Manager has been kept informed about progress and outputs.

During the next reporting period, the objectives include announcing the findings of the Focus Groups and questionnaire.

### 19. Exit/Sustainability Plan

N/A during this reporting period.

## Appendixes

### Appendix A.  Project Budget

| Indicate Reporting Period | YR1 Budget | YR 1 Spend | YR 1 Forecast | YR 1 Balance | YR2 | YR3 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 12 months to 31st May 2006 |  |  |  |  |  |
| Staff (list all staff with FTEs and salary scale range) |  |  |  |  |  |  |  |
| Project Manager: Roddy MacLeod ALC 4 | 5,020 | 7,281 |  |  |  |  |  |
| Project Officer: Malcolm Moffat ALC 2 | 18,545 | 14,486 |  |  |  |  |  |
| Technical Officer: Santiago Chumbe RA2 | 8,711 | 9,084 |  |  |  |  |  |
|  | 32,276 | 30,851 |  |  |  |  |  |
| Travel & Subsistence | 1,000 | 114 |  |  |  |  |  |
| Equipment (items over £10k) |  |  |  |  |  |  |  |
| Dissemination activities |  |  |  |  |  |  |  |
| Evaluation activities |  |  |  |  |  |  |  |
| Other |  |  |  |  |  |  |  |
| Focus Groups/Workshops | 1,000 |  |  |  |  |  |  |
| Partner expenses | 6,600* |  |  |  |  |  |  |
| Training | 500 |  |  |  |  |  |  |
| Office Costs | 2,230 |  |  |  |  |  |  |
| Total from JISC | 43,606 | 30,965 |  |  |  |  |  |

* As a result of Adiuri Systems Ltd going into receivership, £4,000 is unspent from this item, and this amount will be added to Staff costs to take account of additional effort described above in: 2. Aims and Objectives.