11th PERX MEETING: 11 May 2006 @ 14.15 hrs ICBL

MINUTES

Attending: Roddy MacLeod, Malcolm Moffat, Santy Chumbe

Apologies: Roger Rist, Phil Barker

Minutes: RM

- Minutes of the last meeting

The minutes were accepted as accurate.

- Actions and Matters arising

Roddy had consulted with Roger, Neil Jacobs, and Chris McMahon, and it had been agreed in principle to drop Task 35 and consider developing a bid under future calls http://www.jisc.ac.uk/capital_roadmap.html (e.g. the September Call) with respect to work on browsing, clustering results, etc.  Traugott Koch from Ukoln had shown interest in a possible bid.  Chris would like some sample PerX data in the meantime.

Action 1.  Santy to send sample data to Chris McMahon.

Roddy was still trying to retrieve the Consortium Agreement from the people who had taken over Adiuri’s records.

Neil Jacobs had requested a brief change report.

Action 2.  Roddy to send Neil Jacobs a change report.

Mike Chrimes had reported that he was not sure about whether he could send us a text file of the ICE Database.

Action 3. Santy to look at what we can do with the file already sent.

Santy was still writing the paper for ATINER.

Action 4. Santy to circulate draft paper “Overcoming the obstacles of harvesting and searching digital repositories from federated searching toolkits embedded in VLEs” when ready, and get comments from all.

- WorkPackage 2

Malcolm had checked that the most recent targets added (Caltech Earthquake Engineering Research Lab Tech Reports; and Digital Library Network for Engineering and Technology) were working OK.  Workpackage 2 is now complete!

4. WorkPackage 3

The Potential Advocacy document http://www.icbl.hw.ac.uk/perx/advocacyprivate.htm had been updated, but a schedule was still needed.

Action 5.  MM and RM to work out schedule for contacting further targets on the Advocacy List.

Malcolm had contacted Jorum about sets, and was waiting for further responses.  He would also contact ARROW and NDLTD.

Roddy had sent details of Pilot to Philip Pothen for JISC website, and had been publicising its availability to lists (JISC-Repositories, JISC-Development, UKeiG, Lis-Scitech, HEA Engineering, etc).  Items had appeared at: http://www.jisc.ac.uk/index.cfm?name=perx_pilot and Open Access News http://www.bloglines.com/preview?siteid=561274&itemid=4257 Knowledgespeak, eGov http://www.egovmonitor.com/node/5821 ResourceShelf, VIP, DRP Wiki, and Frances Williams would insert something about the 60 Second Survey in a future HW electronic newsletter.  The Pilot had received 13,376 hits from 1,125 visitors in April.

It was agreed that we would wait until there were 100 respondents to the 60 Second Survey before making the draw.

Planning of Focus Groups was underway.  Malcolm had contacted John Harrington and Martin Cooke about holding groups at RSC and Cranfield.  Hopefully all groups would be held by end June.  Malcolm had started on the content.

Action 6. RM to find out the best way to pay for Amazon vouchers for Focus Group attendees.  There would be a maximum of 24 at £50.

5. WorkPackage 4

WRT the IESR work schedule, Malcolm had identified COPAC as a Z target and Jorum as an OAI-PMH target of interest.

Action 7.  MM to follow up as per work schedule, and ask for Jorum to be added to IESR.

Work on the PerX Administrative Interface had started with Malcolm’s wish list.

Santy reported that the PerX software didn’t work very fast with large databases, and we would wait until the SPP work had been done to take a decision regarding Lucene.

6. AOB

Santy, Malcolm and Roddy would try to co-ordinate holidays to ensure that work progressed.

Malcolm reported that he had identified a number of new potential databases.

Action 8.  Once the Focus Groups are completed, MM and RM to look at the list of potential new targets.

Mike Chrimes had requested a meeting with us on 1st or 2nd June to discuss a project being undertaken by Mike Thorne on creating an e-library consortium in civil engineering and the potential of the PerX model.  MM and RM to meet with them.

7. Date of Next Meeting

June 8th 2.15pm, ICBL.